## SWOT
Strengths |  | Weaknesses
| - Work Experience (LGBT Community Center Volunteer) |  | - Low experience in programming
- No experience writing this type of report
- Data Analytics knowledge
- Logical approach
Learned Problem solving techniques
Opportunities |  | Threats
| - Networking |  | - Previous similar work
| - Interest in researching the choosen topic |  | - Large Dataset
| - Identify patterns that might help to explore solutions |  | - Results might not lead any meaningful conclusion

## InOut_Scope
| In Scope |  | Out of Scope
1 | Create Project Management tools | 1 | Analyse data from different countries
2 | Clean the data | 2 | Run a survey
3 | Merge datasets (hate crime + population + gini) | 3 | Create a video for the presentation
4 | Forecaste the data by applying Exp. Smoothing | 4 | Use another software not used in class
5 | Create a Clustering and apply KNN | 5 | Have assistance from another person but Enda
6 | Perform Linear Regression
7 | Webscrap data from Twitter
8 | Create and rank the corpus
9 | Apply NPL - Sentimental Analysis
10 | Create Charts Data Visualization in Excel
11 | Create Tableau Interactive Map Visualization
12 | Perform the analysis of results and findings
13 | Search many different sources of referencing
14 | Create slides presentation
15 | Develop Project Report
16 | Present the Project

## Risk_Priorities
| Risks |  | Priorities
1 | Many different analysis about the topic - Pleogiorism | 1 | Clean the dataset
2 | Not possible to perform enough statistical analysis with the data available | 2 | Establish milestones for each stage of project
3 | Coding issues during analysis | 3 | Continuosly check if activities are not delayed
4 | Difficulties while writing the report | 4 | Manage the risks
5 | Not achiving the expected results | 5 | Not have any plagiarism

## GrantChart_(Schedule)
| Activity |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
| Milestone |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Days off | Status | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08
1 | Project Preparation
1.1 | Find Dataset | Concluded | bar: Week 1 Mon to Week 1 Fri
1.2 | Perform Project Management Tools | Concluded | bar: Week 1 Sat to Week 2 Tue
1.2.1 | Create Project Scope/Out of Scope | Concluded | bar: Week 1 Sat to Week 1 Sun
1.2.2 | Create Project Schedule | Concluded | bar: Week 1 Sat to Week 1 Sun
1.2.3 | Elaborate SWOT | Concluded | bar: Week 2 Mon to Week 2 Tue
1.2.4 | Define Project Risks and Priorities | Concluded | bar: Week 2 Mon to Week 2 Tue
1.3 | Search References I | Concluded | bar: Week 2 Mon to Week 2 Wed
1.4 | Elaborate Project Proposal | Concluded | bar: Week 2 Mon to Week 2 Fri
1.5 | Review PM tools + Proposal | Concluded | bar: Week 2 Sat to Week 2 Sun
1.6 | Project Proposal Submission | Concluded | bar: Week 2 Sun
2 | Project Development I - Analysis
2.1 | Perform Data Cleaning | Concluded | bar: Week 3 Mon
2.1.1 | Import dataset to Rstudio | Concluded | bar: Week 3 Mon
2.1.2 | Preprare R scripts | Concluded | bar: Week 3 Mon
2.1.3 | Remove NAs and irrelevant info | Concluded | bar: Week 3 Mon
2.2 | Perform Statisical Analysis | In Progress | bar: Week 3 Tue to Week 4 Fri
2.2.1 | Check for applicable statistical tests | In Progress | bar: Week 3 Tue to Week 4 Fri
2.2.2 | Create a Clustering and KNN | In Progress | bar: Week 3 Wed to Week 3 Fri
2.2.3 | Apply Decision Tree and Random Forest | Concluded | bar: Week 3 Wed to Week 3 Fri
2.2.4 | Perform other ML techniques | In Progress | bar: Week 3 Wed to Week 4 Fri
2.3 | Perform Web Scrapping | Pending | bar: Week 3 Fri to Week 4 Fri
2.3.1 | Import data from Twitter | Pending | bar: Week 3 Fri to Week 3 Sun
2.3.2 | Create and rank the corpus | Pending | bar: Week 3 Sun to Week 4 Tue
2.3.3 | Apply NPL - Sentimental Analysis | Pending | bar: Week 3 Sun to Week 4 Fri
2.4 | Peform Data Visualization | Pending | bar: Week 5 Mon to Week 5 Fri
2.4.1 | Define data to be represented | Pending | bar: Week 5 Mon
2.4.2 | Create MS Excel Charts | Pending | bar: Week 5 Mon to Week 5 Tue
2.4.3 | Create Tableau Interactive Map Visualization | Pending | bar: Week 5 Mon to Week 5 Fri
3 | Project Development II - Elaboration
3.1 | Elaborate Project Progress Report | In Progress | bar: Week 5 Fri to Week 5 Sun
3.2 | Submit Project Progress Report | In Progress | bar: Week 5 Sun
3.3 | Search References II | Concluded | bar: Week 6 Mon to Week 6 Fri
3.4 | Study the Material (anti-Plagiorism and Referencing) | Concluded | bar: Week 6 Mon to Week 6 Fri
3.5 | Elaborate Project Final Report | In Progress | bar: Week 6 Sat to Week 8 Fri
3.5.1 | Write Section 1 | In Progress | bar: Week 6 Sat to Week 7 Thu
3.5.2 | Write Section 2 | Pending | bar: Week 7 Thu to Week 8 Mon
3.5.3 | Write Section 3 | Pending | bar: Week 8 Mon to Week 8 Fri
3.6 | Elaborate Project Presentation | Pending | bar: Week 9 Mon to Week 9 Fri
4 | Project Conclusion
4.1 | Review Project Report + Presentation | Pending | bar: Week 9 Sat to Week 10 Tue
4.2 | Prepare script for Presentation | Pending | bar: Week 10 Mon to Week 10 Wed
4.3 | Submit Project Report + Presentation | Pending | bar: Week 10 Fri
4.4 | Present the Project | Pending
Note on Q3: Guilherme Arpi: Poject Proposal Deadline
Note on AL3: Guilherme Arpi: Progress Report Deadline
Note on BS3: Guilherme Arpi: Project Report & Presentation Slides Deadline

## MoSCoW
| Must |  | Should
1 | Large Dataset Analysis | 1 | Progress Report
2 | Data cleaning | 2 | SWOT
3 | Machine Learning Algorithms | 3 | Risks and Priorities
4 | Schedule | 4 | Data Visualization charts
5 |  | 5
| Could |  | Won't
1 | Web scrapping from Twitter | 1 | Analyse data from different countries
2 | Query and Rank the corpus | 2 | Run a survey
3 | Sentimental Analyis | 3 | Create a video for the presentation
4 | Interactive Maps | 4 | Use another software not used in class
5 |  | 5 | Have assistance from another person but Enda

## Sheet7 (hidden)
Column1
Concluded
In Progress
Pending